## Backlog
Sprint | Week | Task ID | Task Name | Deliverables
Sprint 1: Foundation & Authentication | Week 1 | W1-T1 | Firebase project initialization with Google OAuth provider configuration | Complete authentication system across all platforms (Web, Mobile, Admin)
Sprint 1: Foundation & Authentication | Week 1 | W1-T2 | Backend server setup with Express 5 and MongoDB connection
Sprint 1: Foundation & Authentication | Week 1 | W1-T3 | User model implementation with Firebase UID integration
Sprint 1: Foundation & Authentication | Week 1 | W1-T4 | Authentication middleware with Firebase token verification
Sprint 1: Foundation & Authentication | Week 1 | W1-T5 | Auth sync endpoint for Firebase-to-MongoDB user synchronization
Sprint 1: Foundation & Authentication | Week 1 | W1-T6 | React web app with glassmorphism dark-green UI design
Sprint 1: Foundation & Authentication | Week 1 | W1-T7 | Login and registration pages for web platform
Sprint 1: Foundation & Authentication | Week 1 | W1-T8 | React Native mobile app initialization with Expo Router
Sprint 1: Foundation & Authentication | Week 1 | W1-T9 | Mobile authentication screens (Login/Register) with Google OAuth support
Sprint 1: Foundation & Authentication | Week 1 | W1-T10 | Firebase Auth integration across all platforms
Sprint 2: Core Academic Features | Week 2 | W2-T1 | Material Hub implementation with Google Drive integration | Material Hub, GPA Calculator, GPA Planner, and Timetable Generator fully functional
Sprint 2: Core Academic Features | Week 2 | W2-T2 | Materials folder and file management system
Sprint 2: Core Academic Features | Week 2 | W2-T3 | Course materials organization with subfolder structure
Sprint 2: Core Academic Features | Week 2 | W2-T4 | GPA Calculator with term GPA and cumulative GPA computation
Sprint 2: Core Academic Features | Week 2 | W2-T5 | GPA Planner with target strategy algorithm
Sprint 2: Core Academic Features | Week 2 | W2-T6 | Smart study plan generation based on course difficulty
Sprint 2: Core Academic Features | Week 2 | W2-T7 | Timetable generator with AI-powered schedule parsing
Sprint 2: Core Academic Features | Week 2 | W2-T8 | Schedule management API with conflict detection
Sprint 2: Core Academic Features | Week 2 | W2-T9 | Frontend pages for Materials, GPA Calculator, and GPA Planner
Sprint 2: Core Academic Features | Week 2 | W2-T10 | Mobile timetable view with weekly schedule display
Sprint 3: Security & Platform Integration | Week 3 | W3-T1 | Custom admin claims implementation in Firebase | Secure admin dashboard with full user management and role-based access control
Sprint 3: Security & Platform Integration | Week 3 | W3-T2 | Role-based access control (admin vs student)
Sprint 3: Security & Platform Integration | Week 3 | W3-T3 | User access status management (active, pending, blocked)
Sprint 3: Security & Platform Integration | Week 3 | W3-T4 | Admin dashboard UI with user management interface
Sprint 3: Security & Platform Integration | Week 3 | W3-T5 | Course and doctor CRUD operations for admins
Sprint 3: Security & Platform Integration | Week 3 | W3-T6 | Course instance management system
Sprint 3: Security & Platform Integration | Week 3 | W3-T7 | API security improvements across all endpoints
Sprint 3: Security & Platform Integration | Week 3 | W3-T8 | Mobile app API integration with backend services
Sprint 3: Security & Platform Integration | Week 3 | W3-T9 | Authentication flow improvements on mobile
Sprint 3: Security & Platform Integration | Week 3 | W3-T10 | Cross-platform data synchronization
Sprint 4: AI Question Generation & Quiz System | Week 4 | W4-T1 | AI-powered question generation system with multiple question types | Complete AI question generation system with MCQ, T/F, Short Answer, and Essay support
Sprint 4: AI Question Generation & Quiz System | Week 4 | W4-T2 | MCQ (Multiple Choice Questions) generation with automatic answer options
Sprint 4: AI Question Generation & Quiz System | Week 4 | W4-T3 | True/False question generation
Sprint 4: AI Question Generation & Quiz System | Week 4 | W4-T4 | Short answer question generation
Sprint 4: AI Question Generation & Quiz System | Week 4 | W4-T5 | Essay question generation with grading rubrics
Sprint 4: AI Question Generation & Quiz System | Week 4 | W4-T6 | Question difficulty level assignment (Easy, Medium, Hard)
Sprint 4: AI Question Generation & Quiz System | Week 4 | W4-T7 | Chapter-based question organization and filtering
Sprint 4: AI Question Generation & Quiz System | Week 4 | W4-T8 | Student interface for generating custom practice questions
Sprint 4: AI Question Generation & Quiz System | Week 4 | W4-T9 | Question bank management and storage
Sprint 4: AI Question Generation & Quiz System | Week 4 | W4-T10 | AI integration with Google Generative AI and OpenAI
Sprint 4: AI Question Generation & Quiz System | Week 4 | W4-T11 | Question editing and refinement capabilities
Sprint 4: AI Question Generation & Quiz System | Week 4 | W4-T12 | Export and sharing functionality for generated questions
Sprint 5: Polish, Security & Production Readiness | Week 5 | W5-T1 | Comprehensive security audit and hardening | Production-ready application with complete security, optimization, and documentation
Sprint 5: Polish, Security & Production Readiness | Week 5 | W5-T2 | Production-ready authentication middleware (disabled test mode)
Sprint 5: Polish, Security & Production Readiness | Week 5 | W5-T3 | Input validation with Joi schemas
Sprint 5: Polish, Security & Production Readiness | Week 5 | W5-T4 | Error handling improvements across all controllers
Sprint 5: Polish, Security & Production Readiness | Week 5 | W5-T5 | CORS configuration with environment-based origins
Sprint 5: Polish, Security & Production Readiness | Week 5 | W5-T6 | Rate limiting for AI endpoints
Sprint 5: Polish, Security & Production Readiness | Week 5 | W5-T7 | Database query optimization and indexing
Sprint 5: Polish, Security & Production Readiness | Week 5 | W5-T8 | Admin dashboard completion with all CRUD operations
Sprint 5: Polish, Security & Production Readiness | Week 5 | W5-T9 | User management with role and status controls
Sprint 5: Polish, Security & Production Readiness | Week 5 | W5-T10 | Final UI/UX polish across all platforms
Sprint 5: Polish, Security & Production Readiness | Week 5 | W5-T11 | Documentation and deployment preparation

## Task Tracking
Task ID | Task Name | Sprint | Week | Status | Assignee | Start Date | End Date | Priority | Notes
W1-T1 | Firebase project initialization with Google OAuth provider configuration | Sprint 1: Foundation & Authentication | Week 1 | To Do |  | 2026-03-14 | 2026-03-20 | High
W1-T2 | Backend server setup with Express 5 and MongoDB connection | Sprint 1: Foundation & Authentication | Week 1 | To Do |  | 2026-03-14 | 2026-03-20 | High
W1-T3 | User model implementation with Firebase UID integration | Sprint 1: Foundation & Authentication | Week 1 | To Do |  | 2026-03-14 | 2026-03-20 | High
W1-T4 | Authentication middleware with Firebase token verification | Sprint 1: Foundation & Authentication | Week 1 | To Do |  | 2026-03-14 | 2026-03-20 | High
W1-T5 | Auth sync endpoint for Firebase-to-MongoDB user synchronization | Sprint 1: Foundation & Authentication | Week 1 | To Do |  | 2026-03-14 | 2026-03-20 | High
W1-T6 | React web app with glassmorphism dark-green UI design | Sprint 1: Foundation & Authentication | Week 1 | To Do |  | 2026-03-14 | 2026-03-20 | High
W1-T7 | Login and registration pages for web platform | Sprint 1: Foundation & Authentication | Week 1 | To Do |  | 2026-03-14 | 2026-03-20 | High
W1-T8 | React Native mobile app initialization with Expo Router | Sprint 1: Foundation & Authentication | Week 1 | To Do |  | 2026-03-14 | 2026-03-20 | High
W1-T9 | Mobile authentication screens (Login/Register) with Google OAuth support | Sprint 1: Foundation & Authentication | Week 1 | To Do |  | 2026-03-14 | 2026-03-20 | High
W1-T10 | Firebase Auth integration across all platforms | Sprint 1: Foundation & Authentication | Week 1 | To Do |  | 2026-03-14 | 2026-03-20 | High
W2-T1 | Material Hub implementation with Google Drive integration | Sprint 2: Core Academic Features | Week 2 | To Do |  | 2026-03-21 | 2026-03-27 | High
W2-T2 | Materials folder and file management system | Sprint 2: Core Academic Features | Week 2 | To Do |  | 2026-03-21 | 2026-03-27 | High
W2-T3 | Course materials organization with subfolder structure | Sprint 2: Core Academic Features | Week 2 | To Do |  | 2026-03-21 | 2026-03-27 | High
W2-T4 | GPA Calculator with term GPA and cumulative GPA computation | Sprint 2: Core Academic Features | Week 2 | To Do |  | 2026-03-21 | 2026-03-27 | High
W2-T5 | GPA Planner with target strategy algorithm | Sprint 2: Core Academic Features | Week 2 | To Do |  | 2026-03-21 | 2026-03-27 | High
W2-T6 | Smart study plan generation based on course difficulty | Sprint 2: Core Academic Features | Week 2 | To Do |  | 2026-03-21 | 2026-03-27 | High
W2-T7 | Timetable generator with AI-powered schedule parsing | Sprint 2: Core Academic Features | Week 2 | To Do |  | 2026-03-21 | 2026-03-27 | High
W2-T8 | Schedule management API with conflict detection | Sprint 2: Core Academic Features | Week 2 | To Do |  | 2026-03-21 | 2026-03-27 | High
W2-T9 | Frontend pages for Materials, GPA Calculator, and GPA Planner | Sprint 2: Core Academic Features | Week 2 | To Do |  | 2026-03-21 | 2026-03-27 | High
W2-T10 | Mobile timetable view with weekly schedule display | Sprint 2: Core Academic Features | Week 2 | To Do |  | 2026-03-21 | 2026-03-27 | High
W3-T1 | Custom admin claims implementation in Firebase | Sprint 3: Security & Platform Integration | Week 3 | To Do |  | 2026-03-28 | 2026-04-03 | Medium
W3-T2 | Role-based access control (admin vs student) | Sprint 3: Security & Platform Integration | Week 3 | To Do |  | 2026-03-28 | 2026-04-03 | Medium
W3-T3 | User access status management (active, pending, blocked) | Sprint 3: Security & Platform Integration | Week 3 | To Do |  | 2026-03-28 | 2026-04-03 | Medium
W3-T4 | Admin dashboard UI with user management interface | Sprint 3: Security & Platform Integration | Week 3 | To Do |  | 2026-03-28 | 2026-04-03 | Medium
W3-T5 | Course and doctor CRUD operations for admins | Sprint 3: Security & Platform Integration | Week 3 | To Do |  | 2026-03-28 | 2026-04-03 | Medium
W3-T6 | Course instance management system | Sprint 3: Security & Platform Integration | Week 3 | To Do |  | 2026-03-28 | 2026-04-03 | Medium
W3-T7 | API security improvements across all endpoints | Sprint 3: Security & Platform Integration | Week 3 | To Do |  | 2026-03-28 | 2026-04-03 | Medium
W3-T8 | Mobile app API integration with backend services | Sprint 3: Security & Platform Integration | Week 3 | To Do |  | 2026-03-28 | 2026-04-03 | Medium
W3-T9 | Authentication flow improvements on mobile | Sprint 3: Security & Platform Integration | Week 3 | To Do |  | 2026-03-28 | 2026-04-03 | Medium
W3-T10 | Cross-platform data synchronization | Sprint 3: Security & Platform Integration | Week 3 | To Do |  | 2026-03-28 | 2026-04-03 | Medium
W4-T1 | AI-powered question generation system with multiple question types | Sprint 4: AI Question Generation & Quiz System | Week 4 | To Do |  | 2026-04-04 | 2026-04-10 | Medium
W4-T2 | MCQ (Multiple Choice Questions) generation with automatic answer options | Sprint 4: AI Question Generation & Quiz System | Week 4 | To Do |  | 2026-04-04 | 2026-04-10 | Medium
W4-T3 | True/False question generation | Sprint 4: AI Question Generation & Quiz System | Week 4 | To Do |  | 2026-04-04 | 2026-04-10 | Medium
W4-T4 | Short answer question generation | Sprint 4: AI Question Generation & Quiz System | Week 4 | To Do |  | 2026-04-04 | 2026-04-10 | Medium
W4-T5 | Essay question generation with grading rubrics | Sprint 4: AI Question Generation & Quiz System | Week 4 | To Do |  | 2026-04-04 | 2026-04-10 | Medium
W4-T6 | Question difficulty level assignment (Easy, Medium, Hard) | Sprint 4: AI Question Generation & Quiz System | Week 4 | To Do |  | 2026-04-04 | 2026-04-10 | Medium
W4-T7 | Chapter-based question organization and filtering | Sprint 4: AI Question Generation & Quiz System | Week 4 | To Do |  | 2026-04-04 | 2026-04-10 | Medium
W4-T8 | Student interface for generating custom practice questions | Sprint 4: AI Question Generation & Quiz System | Week 4 | To Do |  | 2026-04-04 | 2026-04-10 | Medium
W4-T9 | Question bank management and storage | Sprint 4: AI Question Generation & Quiz System | Week 4 | To Do |  | 2026-04-04 | 2026-04-10 | Medium
W4-T10 | AI integration with Google Generative AI and OpenAI | Sprint 4: AI Question Generation & Quiz System | Week 4 | To Do |  | 2026-04-04 | 2026-04-10 | Medium
W4-T11 | Question editing and refinement capabilities | Sprint 4: AI Question Generation & Quiz System | Week 4 | To Do |  | 2026-04-04 | 2026-04-10 | Medium
W4-T12 | Export and sharing functionality for generated questions | Sprint 4: AI Question Generation & Quiz System | Week 4 | To Do |  | 2026-04-04 | 2026-04-10 | Medium
W5-T1 | Comprehensive security audit and hardening | Sprint 5: Polish, Security & Production Readiness | Week 5 | To Do |  | 2026-04-11 | 2026-04-17 | Medium
W5-T2 | Production-ready authentication middleware (disabled test mode) | Sprint 5: Polish, Security & Production Readiness | Week 5 | To Do |  | 2026-04-11 | 2026-04-17 | Medium
W5-T3 | Input validation with Joi schemas | Sprint 5: Polish, Security & Production Readiness | Week 5 | To Do |  | 2026-04-11 | 2026-04-17 | Medium
W5-T4 | Error handling improvements across all controllers | Sprint 5: Polish, Security & Production Readiness | Week 5 | To Do |  | 2026-04-11 | 2026-04-17 | Medium
W5-T5 | CORS configuration with environment-based origins | Sprint 5: Polish, Security & Production Readiness | Week 5 | To Do |  | 2026-04-11 | 2026-04-17 | Medium
W5-T6 | Rate limiting for AI endpoints | Sprint 5: Polish, Security & Production Readiness | Week 5 | To Do |  | 2026-04-11 | 2026-04-17 | Medium
W5-T7 | Database query optimization and indexing | Sprint 5: Polish, Security & Production Readiness | Week 5 | To Do |  | 2026-04-11 | 2026-04-17 | Medium
W5-T8 | Admin dashboard completion with all CRUD operations | Sprint 5: Polish, Security & Production Readiness | Week 5 | To Do |  | 2026-04-11 | 2026-04-17 | Medium
W5-T9 | User management with role and status controls | Sprint 5: Polish, Security & Production Readiness | Week 5 | To Do |  | 2026-04-11 | 2026-04-17 | Medium
W5-T10 | Final UI/UX polish across all platforms | Sprint 5: Polish, Security & Production Readiness | Week 5 | To Do |  | 2026-04-11 | 2026-04-17 | Medium
W5-T11 | Documentation and deployment preparation | Sprint 5: Polish, Security & Production Readiness | Week 5 | To Do |  | 2026-04-11 | 2026-04-17 | Medium